## timeline
# | G | Cat | ST | Task | Fn | Owner | Start | Due | DateST | #d | Notes | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1
[11 empty] | ` | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29
[11 empty] | Date | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29
# | G | Cat | ST | Task | Fn | Owner | Start | Due | DueDate Status | #d | Notes | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa
1 | G3 | MI | OPEN | Assets final MI | MKT |  | 2025-04-23 | 2025-06-30 | CONFIRMED | #d: 46; We: ■; Th: ■; Fr: ■; Mo: ■; We: ■; Th: ■; Fr: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ◆
2 | G3 | Sync | OPEN | Kick off | MKT |  | 2025-05-21 | 2025-05-21 | TENTATIVE | bar: #d; We
3 | G3 | Design | OPEN | BRD creation | MKT |  | 2025-05-07 | 2025-05-21 | TENTATIVE | #d: 11; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ◆
4 | G3 | Sync | OPEN | BRD walkthrough to DG | MKT |  | 2025-05-26 | 2025-05-30 | TENTATIVE | #d: 5; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ◆
5 | G3 | Design | OPEN | DA creation | DG |  | 2025-06-02 | 2025-06-10 | TENTATIVE | #d: 7; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ◆
6 | G3 | Design | OPEN | DP creation | DG |  | 2025-06-02 | 2025-06-10 | TENTATIVE | #d: 7; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ◆
7 | G3 | Sync | OPEN | DP walkthrough | DG |  | 2025-06-10 | 2025-06-10 | TENTATIVE | bar: #d; Tu
8 | G3 | Design | OPEN | IT assessment | IT |  | 2025-06-11 | 2025-06-19 | TENTATIVE | #d: 7; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ◆
9 | G3 | Design | OPEN | User Story creation | IT |  | 2025-06-11 | 2025-06-19 | TENTATIVE | #d: 7; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ◆
10 | G3 | Sync | OPEN | User Story walkthrough | IT |  | 2025-06-11 | 2025-06-19 | TENTATIVE | #d: 7; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ◆
11 | G3 | Sync | OPEN | User Story sign-off / tech req freeze | IT |  | 2025-06-11 | 2025-06-19 | TENTATIVE | #d: 7; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ◆
12 | G3 | Design | OPEN | CO rollout plan | CO |  | 2025-05-22 | 2025-06-19 | TENTATIVE | #d: 21; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ◆
13 | G3 | Confirmation | OPEN | Budget fixed | MKT |  | 2025-06-30 | 2025-06-30 | TENTATIVE | bar: #d; Mo
14 | G3 | Confirmation | OPEN | Go-live date fixed | MKT |  | 2025-06-30 | 2025-06-30 | TENTATIVE | bar: #d; Mo
15 | G3 | Design | OPEN | Biz req lock-in | MKT |  | 2025-06-30 | 2025-06-30 | TENTATIVE | bar: #d; Mo
16 | G3 | Design | OPEN | Biz req lock-in | DG |  | 2025-06-30 | 2025-06-30 | TENTATIVE | bar: #d; Mo
17 | G3 | Design | OPEN | Biz req lock-in | CO |  | 2025-06-30 | 2025-06-30 | TENTATIVE | bar: #d; Mo
18 | G3 | Design | OPEN | Biz req lock-in | IT |  | 2025-06-30 | 2025-06-30 | TENTATIVE | bar: #d; Mo
19 | G3 | Sync | OPEN | MSG approval for the rollout plan | MKT |  | 2025-06-30 | 2025-06-30 | TENTATIVE | bar: #d; Mo
20 | G3 | Sign-off | OPEN | PreG3 Functional Review | IT |  | 2025-07-01 | 2025-07-07 | TENTATIVE | #d: 5; Notes: 2 to 4 weeks; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ◆
21 | G3 | Sign-off | OPEN | PreG3 Functional Review | DG |  | 2025-07-01 | 2025-07-07 | TENTATIVE | #d: 5; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ◆
22 | G3 | Sign-off | OPEN | PreG3 Functional Review | CO |  | 2025-07-01 | 2025-07-07 | TENTATIVE | #d: 5; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ◆
23 | G3 | Sign-off | OPEN | PreG3 Functional Review | MRK |  | 2025-07-01 | 2025-07-07 | TENTATIVE | #d: 5; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ◆
24 | G3 | Sign-off | OPEN | PreG3 Functional Review | EA |  | 2025-07-01 | 2025-07-07 | TENTATIVE | #d: 5; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ◆
25 | G3 | PGCM | OPEN | G3 PGCM | PM |  | 2025-07-14 | 2025-07-14 | TENTATIVE | #d: 1; Notes: at least 1 week from fuctional review completion; Mo: ◆
26 | G5 | Dev | OPEN | IT Dev | IT |  |  |  |  | #d: 0
27 | G5 | Dev | OPEN | Digital Dev | DG |  |  |  |  | #d: 0
28 | G5 | Dev | OPEN | OP prep | CO |  |  |  |  | #d: 0
29 | G5 | Dev | OPEN | QA | DG |  |  |  |  | #d: 0
30 | G5 | Dev | OPEN | SIT | IT |  |  |  |  | #d: 0
31 | G5 | test | OPEN | UAT scenario creation | BA |  |  |  |  | #d: 0
32 | G5 | test | OPEN | UAT sign off | BA |  |  |  |  | #d: 0
33 | G5 | Sign-off | OPEN | Due Diligence | E&C |  | 2025-07-15 | 2025-09-15 | TENTATIVE | #d: 42; Tu: ■; We: ■; Th: ■; Fr: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■
34 | G5 | Sign-off | OPEN | Due Diligence | Law |  | 2025-07-15 | 2025-09-15 | TENTATIVE | #d: 42; Tu: ■; We: ■; Th: ■; Fr: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■
35 | G5 | Sign-off | OPEN | Due Diligence | Data Privacy |  | 2025-07-15 | 2025-09-15 | TENTATIVE | #d: 42; Tu: ■; We: ■; Th: ■; Fr: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■
36 | G5 | Sign-off | OPEN | Due Diligence | Finace |  | 2025-07-15 | 2025-09-15 | TENTATIVE | #d: 42; Tu: ■; We: ■; Th: ■; Fr: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■
37 | G5 | Sign-off | OPEN | Due Diligence | InfoSec |  | 2025-07-15 | 2025-09-15 | TENTATIVE | #d: 42; Tu: ■; We: ■; Th: ■; Fr: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■
38 | G5 | Sign-off | OPEN | Due Diligence | Rick&Control |  | 2025-07-15 | 2025-09-15 | TENTATIVE | #d: 42; Tu: ■; We: ■; Th: ■; Fr: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■
39 | G5 | Sign-off | OPEN | Due Diligence | EA |  | 2025-07-15 | 2025-09-15 | TENTATIVE | #d: 42; Tu: ■; We: ■; Th: ■; Fr: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■; Mo: ■; Tu: ■; We: ■; Th: ■; Fr: ■
40 | G5 | PGCM | OPEN | G5 PGCM | PM |  | 2025-09-22 | 2025-09-22 | TENTATIVE | bar: #d; Mo
41 | G5 | sync | OPEN | Go/no-go decision | PM |  |  |  |  | #d: 0
42 | G5 | sync | OPEN | System cutover | IT |  |  |  |  | #d: 0
43 | G5 | sync | OPEN | Sanity check | IT |  |  |  |  | #d: 0
44 | G5 | launch | OPEN | Go live | MKT |  | 2025-10-08 | 2025-10-08 | CONFIRMED | bar: #d; We
45 | G5 | launch | OPEN | DG release - iqos.jp | DG |  | 2025-10-08 | 2025-10-08 | CONFIRMED | bar: #d; We
46 | G5 | launch | OPEN | DG release - iqosphere | DG |  | 2025-10-08 | 2025-10-08 | CONFIRMED | bar: #d; We
47 | G5 | launch | OPEN | DG release - Instagram | DG |  | 2025-10-08 | 2025-10-08 | CONFIRMED | bar: #d; We
48 | G5 | launch | OPEN | DG release - LINE | DG |  | 2025-10-08 | 2025-10-08 | CONFIRMED | bar: #d; We
49 | G5 | launch | OPEN | DG release - eDM | DG |  | 2025-10-08 | 2025-10-08 | CONFIRMED | bar: #d; We
50 | G5 | launch | OPEN | DG release - ads | DG |  | 2025-10-08 | 2025-10-08 | CONFIRMED | bar: #d; We
51 | G5 | launch | OPEN | commence IMS | CO |  | 2025-10-08 | 2025-10-08 | TENTATIVE | bar: #d; We
52 | G5 | launch | OPEN | CVS | CO |  | 2025-10-08 | 2025-10-08 | TENTATIVE | bar: #d; We
53 | G5 | launch | OPEN | FSS | CO |  | 2025-10-08 | 2025-10-08 | TENTATIVE | bar: #d; We
54 | G5 | launch | OPEN | SiS | CO |  | 2025-10-08 | 2025-10-08 | TENTATIVE | bar: #d; We
55 | G5 | launch | OPEN | iPad tools | CO |  | 2025-10-08 | 2025-10-08 | TENTATIVE | bar: #d; We
56 | G5 | launch | OPEN | HORECA | CO |  | 2025-10-08 | 2025-10-08 | TENTATIVE | bar: #d; We
57 | G5 | launch | OPEN | LAMP | CO |  | 2025-10-08 | 2025-10-08 | TENTATIVE | bar: #d; We
58 | G5 | launch | OPEN | PASPA | CO |  | 2025-10-08 | 2025-10-08 | TENTATIVE | bar: #d; We
59 | G5 | launch | OPEN | Magazine | MKT |  |  |  |  | #d: 0
60 | G7 | post launch | OPEN | hypercare | IT |  |  |  |  | #d: 0
61 | G7 | post launch | OPEN | performance tracking | MKT |  |  |  |  | #d: 0
62 | G7 | PBOS | OPEN | Lession Learned submission | MKT |  | 2026-01-15 | 2026-01-15 | TENTATIVE | #d: 0; Notes: 1.5-3 month from go-live date
63 | G7 | PBOS | OPEN | retrospective | PM |  |  |  |  | #d: 0; Notes: 1.5-3 month from go-live date
64 | G7 | PGCM | OPEN | G7 PGCM | PM |  | 2026-01-19 | 2026-01-19 | TENTATIVE | #d: 0; Notes: within 3 month from go-live

## config
label | value
startDate | 2025-04-23
today | 2025-05-30
IO Function | MKT

## statusTask
STATUS
OPEN
WIP
DONE
CANCELED
ABORTED
ON HOLD
DELAYED
N/A

## statusDate
TENTATIVE
CONFIRMED

## pgcms
-
2025-04-28
2025-05-12
2025-05-26
2025-06-09
2025-06-23
2025-07-14
2025-07-28
2025-08-11
2025-08-25
2025-09-08
2025-09-22
2025-10-14
2025-10-27
2025-11-10
2025-11-25
2025-12-08
2025-12-22
2026-01-05
2026-01-19

## holidays
2025-04-29
2025-05-05
2025-05-06
2025-07-21
2025-08-11
2025-09-15
2025-09-23
2025-10-13
2025-11-03
2025-11-24