## timeline
# | G | Workstream | Cat | ST | Task | Fn | Owner | Start | Due | DateST | Notes | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
Month | time axis 2025-06-01 to 2026-01-07
Day | time axis 2025-06-01 to 2026-01-07
# | G | Workstream | Cat | ST | Task | Fn | Owner | Start | Due | Date ST | Notes | time axis 2025-06-01 to 2026-01-07
| G3 |  | Design | OPEN | Marketing Deck/Asset prep | MKT | Lu |  |  | TENTATIVE
| G3 |  | Sync | OPEN | Kickoff | MKT | Lu | 2025-06-16 | 2025-06-20 | TENTATIVE | bar: 2025-06-16 to 2025-06-20
| G3 |  | Design | OPEN | BRD creation | CO | Miyazaki | 2025-06-21 | 2025-07-18 | TENTATIVE | bar: 2025-06-23 to 2025-06-27; 2025-06-30 to 2025-07-04; 2025-07-07 to 2025-07-11; 2025-07-14 to 2025-07-18
| G3 |  | Sync | OPEN | BRD walkthrough | CO | Miyazaki | 2025-07-18 | 2025-07-22 | TENTATIVE | bar: 2025-07-18; 2025-07-22
| G3 |  | Design | OPEN | AP creation | DG | Bertrand | 2025-07-20 | 2025-08-19 | TENTATIVE | bar: 2025-07-22 to 2025-07-25; 2025-07-28 to 2025-08-01; 2025-08-04 to 2025-08-08; 2025-08-12 to 2025-08-15; 2025-08-18 to 2025-08-19
| G3 |  | Design | OPEN | DP creation | DG | Bertrand | 2025-08-19 | 2025-09-02 | CONFIRMED | bar: 2025-08-19 to 2025-08-22; 2025-08-25 to 2025-08-29; 2025-09-01 to 2025-09-02
| G3 |  | Sync | OPEN | DP walkthrough | DG | Bertrand | 2025-09-03 | 2025-09-05 | CONFIRMED | bar: 2025-09-03 to 2025-09-05
| G3 |  | Design | OPEN | IT assessment | IT | Arun | 2025-09-05 | 2025-09-12 | TENTATIVE | bar: 2025-09-05; 2025-09-08 to 2025-09-12
| G3 |  | Design | OPEN | User Story creation | IT | Arun | 2025-09-12 | 2025-09-26 | TENTATIVE | bar: 2025-09-12; 2025-09-16 to 2025-09-19; 2025-09-22; 2025-09-24 to 2025-09-26
| G3 |  | Sync | OPEN | User Story walkthrough | IT | Arun | 2025-09-29 | 2025-10-03 | TENTATIVE | bar: 2025-09-29 to 2025-10-03
| G3 |  | Sign-Off | OPEN | User Story sign-off / tech req freeze | IT | Arun | 2025-09-29 | 2025-10-03 | TENTATIVE | bar: 2025-09-29 to 2025-10-03
| G3 |  | Confirmation | OPEN | Budget fixed | MKT | Lu | 2025-06-20 | 2025-10-03 | TENTATIVE | bar: 2025-06-20; 2025-06-23 to 2025-06-27; 2025-06-30 to 2025-07-04; 2025-07-07 to 2025-07-11; 2025-07-14 to 2025-07-18; 2025-07-22 to 2025-07-25; 2025-07-28 to 2025-08-01; 2025-08-04 to 2025-08-08; 2025-08-12 to 2025-08-15; 2025-08-18 to 2025-08-22; 2025-08-25 to 2025-08-29; 2025-09-01 to 2025-09-05; 2025-09-08 to 2025-09-12; 2025-09-16 to 2025-09-19; 2025-09-22; 2025-09-24 to 2025-09-26; 2025-09-29 to 2025-10-03
| G3 |  | Confirmation | OPEN | Go-live date fixed | MKT | Lu | 2025-06-20 | 2025-10-03 | TENTATIVE | bar: 2025-06-20; 2025-06-23 to 2025-06-27; 2025-06-30 to 2025-07-04; 2025-07-07 to 2025-07-11; 2025-07-14 to 2025-07-18; 2025-07-22 to 2025-07-25; 2025-07-28 to 2025-08-01; 2025-08-04 to 2025-08-08; 2025-08-12 to 2025-08-15; 2025-08-18 to 2025-08-22; 2025-08-25 to 2025-08-29; 2025-09-01 to 2025-09-05; 2025-09-08 to 2025-09-12; 2025-09-16 to 2025-09-19; 2025-09-22; 2025-09-24 to 2025-09-26; 2025-09-29 to 2025-10-03
| G3 |  | Design | OPEN | Business Requirement lock-in | MKT | Lu | 2025-10-03 | 2025-10-03 | TENTATIVE | bar: 2025-10-03
| G3 |  | Design | OPEN | Business Requirement lock-in | CO | Miyazaki | 2025-10-03 | 2025-10-03 | TENTATIVE | bar: 2025-10-03
| G3 |  | Design | OPEN | Business Requirement lock-in | DG | Bertrand | 2025-10-03 | 2025-10-03 | TENTATIVE | bar: 2025-10-03
| G3 |  | Design | OPEN | Business Requirement lock-in | IT | Arun | 2025-10-03 | 2025-10-03 | TENTATIVE | bar: 2025-10-03
| G3 |  | Sign-Off | OPEN | Go-live date fixed | MKT | Lu | 2025-10-03 | 2025-10-03 | TENTATIVE | bar: 2025-10-03
| G3 |  | Sync | OPEN | MT meeting/IO Fn Approval | MKT | Lu | 2025-09-26 | 2025-10-03 | TENTATIVE | bar: 2025-09-26; 2025-09-29 to 2025-10-03
| G3 |  | Sign-Off | OPEN | PreG3 Functional Review | IT | Arun | 2025-10-01 | 2025-10-07 | TENTATIVE | 2 to 4 weeks | bar: 2025-10-01 to 2025-10-03; 2025-10-06 to 2025-10-07
| G3 |  | Sign-Off | OPEN | PreG3 Functional Review | DG | Bertrand | 2025-10-01 | 2025-10-07 | TENTATIVE | bar: 2025-10-01 to 2025-10-03; 2025-10-06 to 2025-10-07
| G3 |  | Sign-Off | OPEN | PreG3 Functional Review | CO | Miyazaki | 2025-10-01 | 2025-10-07 | TENTATIVE | bar: 2025-10-01 to 2025-10-03; 2025-10-06 to 2025-10-07
| G3 |  | Sign-Off | OPEN | PreG3 Functional Review | MRK | Lu | 2025-10-01 | 2025-10-07 | TENTATIVE | bar: 2025-10-01 to 2025-10-03; 2025-10-06 to 2025-10-07
| G3 |  | Sign-Off | OPEN | PreG3 Functional Review | EA |  | 2025-10-01 | 2025-10-07 | TENTATIVE | bar: 2025-10-01 to 2025-10-03; 2025-10-06 to 2025-10-07
| G3 |  | PGCM | OPEN | G3 PGCM | PM | Ken | 2025-10-14 | 2025-10-14 | TENTATIVE | at least 1 week from fuctional review completion | bar: 2025-10-14
| G5 |  | Dev | OPEN | IT Dev | IT | Arun |  |  | TENTATIVE
| G5 |  | Dev | OPEN | Digital Dev | DG | Bertrand |  |  | TENTATIVE
| G5 |  | Dev | OPEN | OP prep | CO | Miyazaki |  |  | TENTATIVE
| G5 |  | Dev | OPEN | QA | IT | Arun |  |  | TENTATIVE
| G5 |  | Dev | OPEN | SIT | IT | Arun |  |  | TENTATIVE
| G5 |  | test | OPEN | UAT | BA |  |  |  | TENTATIVE
| G5 |  | test | OPEN | UAT sign off | BA |  | 2025-11-21 | 2025-11-21 | TENTATIVE | bar: 2025-11-21
| G5 |  | Sign-Off | OPEN | Due Diligence | E&C |  | 2025-11-04 | 2025-11-18 | TENTATIVE | bar: 2025-11-04 to 2025-11-07; 2025-11-10 to 2025-11-14; 2025-11-17 to 2025-11-18
| G5 |  | Sign-Off | OPEN | Due Diligence | Law |  | 2025-11-04 | 2025-11-18 | TENTATIVE | bar: 2025-11-04 to 2025-11-07; 2025-11-10 to 2025-11-14; 2025-11-17 to 2025-11-18
| G5 |  | Sign-Off | OPEN | Due Diligence | DATAPRIVACY |  | 2025-11-04 | 2025-11-18 | TENTATIVE | bar: 2025-11-04 to 2025-11-07; 2025-11-10 to 2025-11-14; 2025-11-17 to 2025-11-18
| G5 |  | Sign-Off | OPEN | Due Diligence | FINANCE |  | 2025-11-04 | 2025-11-18 | TENTATIVE | bar: 2025-11-04 to 2025-11-07; 2025-11-10 to 2025-11-14; 2025-11-17 to 2025-11-18
| G5 |  | Sign-Off | OPEN | Due Diligence | INFOSEC |  | 2025-11-04 | 2025-11-18 | TENTATIVE | bar: 2025-11-04 to 2025-11-07; 2025-11-10 to 2025-11-14; 2025-11-17 to 2025-11-18
| G5 |  | Sign-Off | OPEN | Due Diligence | RISK&CONTROL |  | 2025-11-04 | 2025-11-18 | TENTATIVE | bar: 2025-11-04 to 2025-11-07; 2025-11-10 to 2025-11-14; 2025-11-17 to 2025-11-18
| G5 |  | Sign-Off | OPEN | Due Diligence | EA |  | 2025-11-04 | 2025-11-18 | TENTATIVE | bar: 2025-11-04 to 2025-11-07; 2025-11-10 to 2025-11-14; 2025-11-17 to 2025-11-18
| G5 |  | PGCM | OPEN | G5 PGCM | PM | Ken | 2025-11-25 | 2025-11-25 | TENTATIVE | bar: 2025-11-25
| G5 |  | Sign-Off | OPEN | Go/no-go decision | PM | Ken | 2025-12-01 | 2025-12-04 | TENTATIVE | bar: 2025-12-01 to 2025-12-04
| G5 |  | sync | OPEN | System cutover | IT | Arun | 2025-12-08 | 2025-12-08 | TENTATIVE | bar: 2025-12-08
| G5 |  | sync | OPEN | Sanity check | IT | Arun | 2025-12-09 | 2025-12-09 | TENTATIVE | bar: 2025-12-09
| G5 |  | Sign-Off | OPEN | Go live | PM | Ken | 2025-12-08 | 2025-12-08 | CONFIRMED | bar: 2025-12-08
| G5 |  | launch | OPEN | DG release | DG | Bertrand |  |  | TENTATIVE
| G5 |  | launch | OPEN | commence IMS | CO | Miyazaki |  |  | TENTATIVE
| G7 |  | post launch | OPEN | hypercare | IT | Arun |  |  | TENTATIVE | 1 month
| G7 |  | post launch | OPEN | performance tracking | MKT | Lu |  |  | TENTATIVE | 1 month
| G7 |  | PBOS | OPEN | Lession Learned submission | MKT | Lu |  |  | TENTATIVE | 1.5-3 month from go-live date
| G7 |  | PBOS | OPEN | retrospective | MKT | Lu |  |  | TENTATIVE | 1.5-3 month from go-live date
| G7 |  | Sign-Off | OPEN | G7 PGCM | PM | Ken | - | - |  | within 3 month from go-live

## holidays
2025-04-29
2025-05-05
2025-05-06
2025-07-21
2025-08-11
2025-09-15
2025-09-23
2025-10-13
2025-11-03
2025-11-24

## config
label | value
startDate | 2025-06-01
today | 2025-05-30
IO Function | MKT

## pgcms
-
2025-04-28
2025-05-12
2025-05-26
2025-06-09
2025-06-23
2025-07-14
2025-07-28
2025-08-11
2025-08-25
2025-09-08
2025-09-22
2025-10-14
2025-10-27
2025-11-10
2025-11-25
2025-12-08

## status
STATUS
OPEN
WIP
DONE
CANCELED
ABORTED
ON HOLD
DELAYED
N/A

## DTstatus
TENTATIVE
CONFIRMED