## timeline
# | G | Cat | ST | Task | Fn | Owner | Start | Due | DateST | Notes | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
[10 empty] | Month | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21
[10 empty] | Day | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21
# | G | Cat | ST | Task | Fn | Owner | Start | Due | Date ST | Notes | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr
| G0 | PBOS | DONE | PBOS submission | CO |  | 2025-03-07 | 2025-03-07 | CONFIRMED
| G0 | Review | DONE | Sponsor Endorsement | CO |  | 2025-04-08 | 2025-04-08 | CONFIRMED
| G0 | Review | DONE | PMO Review | PMO |  | 2025-04-22 | 2025-04-22 | CONFIRMED | [8 empty] | ◆
| G0 | Review | DONE | PreG0 Functional Review | IT |  | 2025-04-17 | 2025-04-21 | CONFIRMED | 1 to 2 weeks |  |  | ■ | ■ |  |  | ◆
| G0 | Review | DONE | PreG0 Functional Review | DG |  | 2025-04-17 | 2025-04-21 | CONFIRMED |  |  |  | ■ | ■ |  |  | ◆
| G0 | Review | DONE | PreG0 Functional Review | CO |  | 2025-04-17 | 2025-04-21 | CONFIRMED |  |  |  | ■ | ■ |  |  | ◆
| G0 | Review | N/A | PreG0 Functional Review | MRK |  |  | 2025-04-21
| G0 | Review | N/A | PreG0 Functional Review | EA |  |  | 2025-04-21
| G0 | PGCM | DONE | G0 PGCM | PM |  | 2025-04-28 | 2025-04-28 | CONFIRMED | at least 1 week from fuctional review completion | [13 empty] | ◆
| G3 | Design | N/A | DA creation | DG |  | 2025-05-09 | 2025-05-16 | TENTATIVE
| G3 | Design | N/A | DP creation | DG |  | 2025-05-09 | 2025-05-16 | TENTATIVE
| G3 | Design | DONE | IT assessment for Req #1-4 | IT | Amit | 2025-05-09 | 2025-06-05 | CONFIRMED | [25 empty] | ■ |  |  | ■ | ■ | ■ | ■ | ■ |  |  | ■ | ■ | ■ | ■ | ■ |  |  | ■ | ■ | ■ | ■ | ■ |  |  | ■ | ■ | ■ | ◆
| G3 | Sync | N/A | DP walkthrough | DG |  | 2025-05-09 | 2025-05-16 | TENTATIVE
| G3 | Confirmation | N/A | Budget fixed | CO
| G3 | Confirmation | DONE | Go-live date fixed | CO | Sugo | 2025-05-23 | 2025-05-23 | CONFIRMED | [39 empty] | ◆
| G3 | Design | N/A | Business Requirement lock-in | MKT
| G3 | Design | DONE | Business Requirement lock-in | CO | Sugo | 2025-05-16 | 2025-05-16 | CONFIRMED | [32 empty] | ◆
| G3 | Design | N/A | Business Requirement lock-in | DG |  | 2025-05-16 | 2025-05-20 | TENTATIVE
| G3 | Design | WIP | Business Requirement lock-in | IT | Amit | 2025-05-16 | 2025-06-05 | CONFIRMED | [32 empty] | ■ |  |  | ■ | ■ | ■ | ■ | ■ |  |  | ■ | ■ | ■ | ■ | ■ |  |  | ■ | ■ | ■ | ◆
| G3 | Sync | N/A | MT meeting | CO | Hayashi | 2025-05-20 | 2025-05-20 | CONFIRMED
| G3 | Review | DONE | PreG3 Functional Review | IT | Amit | 2025-05-20 | 2025-05-22 | CONFIRMED | 2 to 4 weeks | [35 empty] | ■ | ■ | ◆
| G3 | Review | DONE | PreG3 Functional Review | DG | Hayashi | 2025-05-20 | 2025-05-22 | TENTATIVE | [36 empty] | ■ | ■ | ◆
| G3 | Review | DONE | PreG3 Functional Review | CO | Miyazaki | 2025-05-20 | 2025-05-22 | CONFIRMED | [36 empty] | ■ | ■ | ◆
| G3 | Review | N/A | PreG3 Functional Review | MRK |  | 2025-05-19 | 2025-05-22
| G3 | Review | N/A | PreG3 Functional Review | EA |  | 2025-05-19 | 2025-05-22
| G3 | PGCM | WIP | G3 PGCM | PM | Ken | 2025-05-26 | 2025-05-26 | CONFIRMED | at least 1 week from fuctional review completion | [41 empty] | ◆
| G3 | Sync | WIP | IT assessment for Req#5 | IT | Amit | 2025-05-16 | 2025-06-05 | CONFIRMED | [32 empty] | ■ |  |  | ■ | ■ | ■ | ■ | ■ |  |  | ■ | ■ | ■ | ■ | ■ |  |  | ■ | ■ | ■ | ◆
| G3 | Sync | N/A | User Story creation | IT
| G3 | Sync | N/A | User Story walkthrough | IT
| G3 | Sync | N/A | User Story sign-off / tech req freeze | IT
| G5 | Dev | OPEN | IT Dev for phase1 | IT | Amit | 2025-05-28 | 2025-06-20 | CONFIRMED | [44 empty] | ■ | ■ | ■ |  |  | ■ | ■ | ■ | ■ | ■ |  |  | ■ | ■ | ■ | ■ | ■ |  |  | ■ | ■ | ■ | ■ | ◆
| G5 | Dev | N/A | Digital Dev | DG
| G5 | Dev | N/A | OP prep | CO
| G5 | Dev | N/A | QA for phase1 | IT
| G5 | Dev | N/A | SIT | IT
| G5 | Dev | OPEN | IT Dev for phase2 | IT | Amit | 2025-06-20 | 2025-08-29 | CONFIRMED
| G5 | test | OPEN | UAT for phase1 | IT | Amit | 2025-06-20 | 2025-06-23 | CONFIRMED | [67 empty] | ■ |  |  | ◆
| G5 | test | OPEN | UAT for phase2 | IT | Amit | 2025-08-30 | 2025-09-08 | CONFIRMED | [140 empty] | ■ | ■ | ■ | ■ | ■ |  |  | ◆
| G5 | sing-off | OPEN | UAT sign off phase1 | CO | Sugo | 2025-06-23 | 2025-06-24 | CONFIRMED | [70 empty] | ■ | ◆
| G5 | sing-off | OPEN | UAT sign off phase2 | CO | Sugo | 2025-09-09 | 2025-09-12 | CONFIRMED | [148 empty] | ■ | ■ | ■ | ◆
| G5 | sing-off | OPEN | Due Diligence | E&C |  | 2025-06-09 | 2025-06-16 | TENTATIVE | [56 empty] | ■ | ■ | ■ | ■ | ■ |  |  | ◆
| G5 | sing-off | OPEN | Due Diligence | LAW |  | 2025-06-09 | 2025-06-16 | TENTATIVE | [56 empty] | ■ | ■ | ■ | ■ | ■ |  |  | ◆
| G5 | sing-off | OPEN | Due Diligence | DATAPRIVACY |  | 2025-06-09 | 2025-06-16 | TENTATIVE | [56 empty] | ■ | ■ | ■ | ■ | ■ |  |  | ◆
| G5 | sing-off | OPEN | Due Diligence | FINANCE |  | 2025-06-09 | 2025-06-16 | TENTATIVE | [56 empty] | ■ | ■ | ■ | ■ | ■ |  |  | ◆
| G5 | sing-off | OPEN | Due Diligence | INFOSEC |  | 2025-06-09 | 2025-06-16 | TENTATIVE | [56 empty] | ■ | ■ | ■ | ■ | ■ |  |  | ◆
| G5 | sing-off | OPEN | Due Diligence | RISK&CONTROL |  | 2025-06-09 | 2025-06-16 | TENTATIVE | [56 empty] | ■ | ■ | ■ | ■ | ■ |  |  | ◆
| G5 | sing-off | OPEN | Due Diligence | EA |  | 2025-06-09 | 2025-06-16 | TENTATIVE | [56 empty] | ■ | ■ | ■ | ■ | ■ |  |  | ◆
| G5 | PGCM | OPEN | G5 PGCM | PM |  | 2025-06-23 | 2025-06-23 | CONFIRMED | [70 empty] | ◆
| G5 | sync | OPEN | Go/no-go decision for phase1 | PM |  | 2025-06-26 | 2025-06-27 | CONFIRMED | [73 empty] | ■ | ◆
| G5 | sync | OPEN | System cutover | IT
| G5 | sync | OPEN | Sanity check | IT
| G5 | launch | OPEN | Go live for phase1 | CO |  | 2025-06-30 | 2025-06-30 | CONFIRMED | [77 empty] | ◆
| G5 | launch | N/A | DG release | DG
| G5 | launch | N/A | commence IMS | CO
| G5 | sync | OPEN | Go/no-go decision for phase2 | PM |  | 2025-09-11 | 2025-09-16 | CONFIRMED | [150 empty] | ■ | ■ |  |  |  | ◆
| G5 | launch | OPEN | Go live for phase2 | CO |  | 2025-09-17 | 2025-09-17 | CONFIRMED | [156 empty] | ◆
| G7 | post launch | OPEN | hypercare | IT |  |  |  |  | 1 month
| G7 | post launch | OPEN | performance tracking | CO |  |  |  |  | 1 month
| G7 | PBOS | OPEN | Lession Learned submission | CO |  | 2025-10-30 | 2025-10-30 | CONFIRMED | 1.5-3 month from go-live date | [198 empty] | ◆
| G7 | PBOS | N/A | retrospective | [5 empty] | 1.5-3 month from go-live date
| G7 | PGCM | OPEN | G7 PGCM | PM |  | 2025-11-10 | 2025-11-10 | CONFIRMED | within 3 month from go-live | [209 empty] | ◆

## config
label | value
startDate | 2025-04-15
today | 2025-05-30
IO Function | CO

## holidays
2025-04-29
2025-05-05
2025-05-06
2025-07-21
2025-08-11
2025-09-15
2025-09-23
2025-10-13
2025-11-03
2025-11-24

## status
STATUS
OPEN
WIP
DONE
CANCELED
ABORTED
ON HOLD
DELAYED
N/A

## pgcms
-
2025-04-28
2025-05-12
2025-05-26
2025-06-09
2025-06-23
2025-07-14
2025-07-28
2025-08-11
2025-08-25
2025-09-08
2025-09-22
2025-10-14
2025-10-27
2025-11-10
2025-11-25
2025-12-08