## timeline
# | G | Cat | ST | Task | Fn | Owner | Start | Due | Date ST | #d | Notes | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
# | G | Cat | ST | Task | Fn | Owner | Start | Due | Date ST | #d | Month | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21
[11 empty] | Day | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21
# | G | Cat | ST | Task | Fn | Owner | Start | Due | Date ST | #d | Notes | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr
| G0 | PBOS | DONE | PBOS submission | CO |  | 2025-03-07 | 2025-03-07 |  | 0
| G0 | Review | DONE | Sponsor Endorsement | CO |  | 2025-04-08 | 2025-04-08 |  | 0
| G0 | Review | DONE | PMO Review | PMO |  | 2025-04-15 | 2025-04-15 |  | 1 |  | ◆
| G0 | Review | DONE | PreG0 Functional Review | IT |  | 2025-04-21 | 2025-04-21 |  | 1 | 1 to 2 weeks | [6 empty] | ◆
| G0 | Review | DONE | PreG0 Functional Review | DG |  | 2025-04-21 | 2025-04-21 |  | 1 | [7 empty] | ◆
| G0 | Review | DONE | PreG0 Functional Review | CO |  | 2025-04-21 | 2025-04-21 |  | 1 | [7 empty] | ◆
| G0 | Review | N/A | PreG0 Functional Review | MRK |  | 2025-04-21 | 2025-04-21 |  | 0
| G0 | Review | N/A | PreG0 Functional Review | EA |  | 2025-04-21 | 2025-04-21 |  | 0
| G0 | PGCM | DONE | G0 PGCM | PM |  | 2025-04-28 | 2025-04-28 |  | 0 | at least 1 week from fuctional review completion | [13 empty] | ◆
| G3 | Sync | N/A | Kickoff | CO |  |  |  |  | 0
| G3 | Sync | DONE | BRD creation | CO |  | 2025-05-02 | 2025-05-02 |  | 0 | [18 empty] | ◆
| G3 | Sync | DONE | BRD walkthrough | CO |  | 2025-05-02 | 2025-05-02 |  | 0 | Already done befoe this stage | [17 empty] | ◆
| G3 | Design | N/A | DA creation | DG |  |  |  |  | 0
| G3 | Design | N/A | DP creation | DG |  |  |  |  | 0
| G3 | Sync | DONE | IT assessment | IT |  | 2025-05-07 | 2025-05-07 |  | 0 | Already done befoe this stage | [22 empty] | ◆
| G3 | Sync | N/A | DP walkthrough | DG |  |  |  |  | 0
| G3 | Confirmation | N/A | Budget fixed | CO |  |  |  |  | 0
| G3 | Confirmation | OPEN | Go-live date fixed | CO |  | 2025-05-07 | 2025-05-07 |  | 0 | [23 empty] | ◆
| G3 | Design | N/A | Business Requirement lock-in | MKT |  |  |  |  | 0
| G3 | Design | DONE | Business Requirement lock-in | CO |  | 2025-05-02 | 2025-05-02 |  | 0 | [18 empty] | ◆
| G3 | Design | N/A | Business Requirement lock-in | DG |  |  |  |  | 0
| G3 | Design | OPEN | Business Requirement lock-in | IT |  |  |  |  | 0
| G3 | Confirmation | OPEN | Go-live date fixed | CO |  |  |  |  | 0
| G3 | Sync | N/A | MT meeting | CO |  |  |  |  | 0
| G3 | Review | OPEN | PreG3 Functional Review | IT |  | 2025-05-07 | 2025-05-08 |  | 0 | 2 to 4 weeks | [22 empty] | ■ | ◆
| G3 | Review | N/A | PreG3 Functional Review | DG |  |  | 2025-05-05 |  | 0
| G3 | Review | DONE | PreG3 Functional Review | CO |  | 2025-05-02 | 2025-05-02 |  | 0 | [18 empty] | ◆
| G3 | Review | N/A | PreG3 Functional Review | MRK |  |  | 2025-05-05 |  | 0
| G3 | Review | N/A | PreG3 Functional Review | EA |  |  | 2025-05-05 |  | 0
| G3 | PGCM | OPEN | G3 PGCM | PM |  | 2025-05-12 | 2025-05-12 |  | 0 | at least 1 week from fuctional review completion | [27 empty] | ◆
| G3 | Sync | OPEN | IT detailed assessment | IT |  |  |  |  | 0
| G3 | Sync | OPEN | User Story creation | IT |  |  |  |  | 0
| G3 | Sync | OPEN | User Story walkthrough | IT |  |  |  |  | 0
| G3 | Sync | OPEN | User Story sign-off / tech req freeze | IT |  |  |  |  | 0
| G5 | Dev | OPEN | IT Dev | IT |  |  |  |  | 0
| G5 | Dev | OPEN | Digital Dev | DG |  |  |  |  | 0
| G5 | Dev | OPEN | OP prep | CO |  |  |  |  | 0
| G5 | Dev | OPEN | QA | IT |  |  |  |  | 0
| G5 | Dev | OPEN | SIT | IT |  |  |  |  | 0
| G5 | test | OPEN | UAT | BA |  |  |  |  | 0
| G5 | test | OPEN | UAT sign off | BA |  |  |  |  | 0
| G5 | Due Diligence | OPEN | E&C | PM |  |  | 2025-05-19 |  | 0
| G5 | Due Diligence | OPEN | Law | PM |  |  | 2025-05-19 |  | 0
| G5 | Due Diligence | OPEN | Data Privacy | PM |  |  | 2025-05-19 |  | 0
| G5 | Due Diligence | OPEN | Finace | PM |  |  | 2025-05-19 |  | 0
| G5 | Due Diligence | OPEN | InfoSec | PM |  |  | 2025-05-19 |  | 0
| G5 | Due Diligence | OPEN | Rick&Control | PM |  |  | 2025-05-19 |  | 0
| G5 | Due Diligence | OPEN | EA | PM |  |  | 2025-05-19 | TENTATIVE | 0
| G5 | PGCM | OPEN | G5 PGCM | PM |  | 2025-05-26 | 2025-05-26 |  | 0 | [42 empty] | ◆
| G5 | sync | OPEN | Go/no-go decision | PM |  |  |  |  | 0
| G5 | sync | OPEN | System cutover | IT |  |  |  |  | 0
| G5 | sync | OPEN | Sanity check | IT |  |  |  |  | 0
| G5 | launch | OPEN | Go live |  |  | 2025-05-27 | 2025-05-27 | CONFIRMED | 0 | [43 empty] | ◆
| G5 | launch | OPEN | DG release | DG |  |  |  |  | 0
| G5 | launch | OPEN | commence IMS | CO |  |  |  |  | 0
| G7 | post launch | OPEN | hypercare | IT |  |  |  |  | 0 | 1 month
| G7 | post launch | OPEN | performance tracking | [5 empty] | 0 | 1 month
| G7 | PBOS | OPEN | Lession Learned submission |  |  | 2025-05-27 | 2025-06-26 |  | 0 | 1.5-3 month from go-live date | [42 empty] | ■ | ■ | ■ | ■ |  |  | ■ | ■ | ■ | ■ | ■ |  |  | ■ | ■ | ■ | ■ | ■ |  |  | ■ | ■ | ■ | ■ | ■ |  |  | ■ | ■ | ■ | ◆
| G7 | PBOS | OPEN | retrospective | [5 empty] | 0 | 1.5-3 month from go-live date
| G7 | PGCM | OPEN | G7 PGCM | PM |  | 2025-07-14 | 2025-07-14 |  | 0 | within 3 month from go-live | [90 empty] | ◆

## holidays
2025-04-29
2025-05-05
2025-05-06
2025-07-21
2025-08-11
2025-09-15
2025-09-23
2025-10-13
2025-11-03
2025-11-24

## config
label | value
startDate | 2025-04-15
today | 2025-05-30
IO Function | CO

## pgcms
-
2025-04-28
2025-05-12
2025-05-26
2025-06-09
2025-06-23
2025-07-14
2025-07-28
2025-08-11
2025-08-25
2025-09-08
2025-09-22
2025-10-14
2025-10-27
2025-11-10
2025-11-25
2025-12-08

## status
STATUS
OPEN
WIP
DONE
CANCELED
ABORTED
ON HOLD
DELAYED
N/A

## DTstatus
TENTATIVE
CONFIRMED