## timeline
# | G | Cat | ST | Task | Fn | Owner | Start | Due | DateST | #d | #d from today | Notes | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Month | time axis 2025-04-15 to 2025-11-21
Day | time axis 2025-04-15 to 2025-11-21
# | G | Cat | ST | Task | Fn | Owner | Start | Due | Date ST | #d | #d from today | Notes | time axis 2025-04-15 to 2025-11-21
| G3 | Sync | OPEN | Kickoff | MKT |  |  |  |  | 0
| G3 | Sync | OPEN | BRD creation | MKT |  |  |  |  | 0
| G3 | Sync | OPEN | BRD walkthrough | MKT |  |  |  |  | 0
| G3 | Design | OPEN | DA creation | DG |  |  |  |  | 0
| G3 | Design | OPEN | DP creation | DG |  |  |  |  | 0
| G3 | Sync | OPEN | IT assessment | IT |  |  |  |  | 0
| G3 | Sync | OPEN | DP walkthrough | DG |  |  |  |  | 0
| G3 | Confirmation | OPEN | Budget fixed | MKT |  |  |  |  | 0
| G3 | Confirmation | OPEN | Go-live date fixed | MKT |  |  |  |  | 0
| G3 | Design | OPEN | Business Requirement lock-in | MKT |  |  |  |  | 0
| G3 | Design | OPEN | Business Requirement lock-in | MKT |  |  |  |  | 0
| G3 | Design | OPEN | Business Requirement lock-in | DG |  |  |  |  | 0
| G3 | Design | OPEN | Business Requirement lock-in | IT |  |  |  |  | 0
| G3 | Confirmation | OPEN | Go-live date fixed | MKT |  |  |  |  | 0
| G3 | Sync | OPEN | MT meeting | MKT |  |  |  |  | 0
| G3 | Review | OPEN | PreG3 Functional Review | IT |  |  | 2025-05-19 |  | 0 |  | 2 to 4 weeks
| G3 | Review | OPEN | PreG3 Functional Review | DG |  |  | 2025-05-19 |  | 0
| G3 | Review | OPEN | PreG3 Functional Review | CO |  |  | 2025-05-19 |  | 0
| G3 | Review | OPEN | PreG3 Functional Review | MRK |  |  | 2025-05-19 |  | 0
| G3 | Review | OPEN | PreG3 Functional Review | EA |  |  | 2025-05-19 |  | 0
| G3 | PGCM | OPEN | G3 PGCM | PM |  | 2025-05-26 | 2025-05-26 |  | 0 |  | at least 1 week from fuctional review completion | bar: 2025-05-26
| G3 | Sync | OPEN | IT detailed assessment | IT |  |  |  |  | 0
| G3 | Sync | OPEN | User Story creation | IT |  |  |  |  | 0
| G3 | Sync | OPEN | User Story walkthrough | IT |  |  |  |  | 0
| G3 | Sync | OPEN | User Story sign-off / tech req freeze | IT |  |  |  |  | 0
| G5 | Dev | OPEN | IT Dev | IT |  |  |  |  | 0
| G5 | Dev | OPEN | Digital Dev | DG |  |  |  |  | 0
| G5 | Dev | OPEN | OP prep | CO |  |  |  |  | 0
| G5 | Dev | OPEN | QA | IT |  |  |  |  | 0
| G5 | Dev | OPEN | SIT | IT |  |  |  |  | 0
| G5 | test | OPEN | UAT | BA |  |  |  |  | 0
| G5 | test | OPEN | UAT sign off | BA |  |  |  |  | 0
| G5 | Due Diligence | OPEN | E&C | PM |  |  | 2025-06-16 |  | 0
| G5 | Due Diligence | OPEN | Law | PM |  |  | 2025-06-16 |  | 0
| G5 | Due Diligence | OPEN | Data Privacy | PM |  |  | 2025-06-16 |  | 0
| G5 | Due Diligence | OPEN | Finace | PM |  |  | 2025-06-16 |  | 0
| G5 | Due Diligence | OPEN | InfoSec | PM |  |  | 2025-06-16 |  | 0
| G5 | Due Diligence | OPEN | Rick&Control | PM |  |  | 2025-06-16 |  | 0
| G5 | Due Diligence | OPEN | EA | PM |  |  | 2025-06-16 |  | 0
| G5 | PGCM | OPEN | G5 PGCM | PM |  | 2025-06-23 | 2025-06-23 |  | 0 | bar: 2025-06-23
| G5 | sync | OPEN | Go/no-go decision | PM |  |  |  |  | 0
| G5 | sync | OPEN | System cutover | IT |  | 2025-06-30 | 2025-06-30 |  | 0 | bar: 2025-06-30
| G5 | sync | OPEN | Sanity check | IT |  |  |  |  | 0
| G5 | launch | N/A | Go live - DC and CVS | CO |  |  |  |  | 0
| G5 | launch | N/A | EC IMS | DG |  |  |  |  | 0
| G5 | launch | N/A | MD slot | CO |  |  |  |  | 0
| G7 | post launch | N/A | hypercare | IT |  |  |  |  | 0 |  | 1 month
| G7 | post launch | N/A | performance tracking | [5 empty] | 0 |  | 1 month
| G7 | PBOS | OPEN | Lession Learned submission | [5 empty] | 0 |  | 1.5-3 month from go-live date
| G7 | PBOS | N/A | retrospective | [5 empty] | 0 |  | 1.5-3 month from go-live date
| G7 | PGCM | OPEN | G7 PGCM | PM |  | - | - |  | 0 |  | within 3 month from go-live

## config
label | value
startDate | 2025-04-15
today | 2025-05-30
IO Function | MKT

## holidays
2025-04-29
2025-05-05
2025-05-06
2025-07-21
2025-08-11
2025-09-15
2025-09-23
2025-10-13
2025-11-03
2025-11-24

## status
STATUS
OPEN
WIP
DONE
CANCELED
ABORTED
ON HOLD
DELAYED
N/A

## pgcms
-
2025-04-28
2025-05-12
2025-05-26
2025-06-09
2025-06-23
2025-07-14
2025-07-28
2025-08-11
2025-08-25
2025-09-08
2025-09-22
2025-10-14
2025-10-27
2025-11-10
2025-11-25
2025-12-08